## Sheet1
Task | Assigned to | Date | Completed by | On date
Professional Mockup | Sallah & Adam | 2024-10-01 | Sallah | 2024-10-03 | Instructions
Scheduling the first team meeting | Samarth & sallah | 2024-09-30 | Samarth | 2024-10-01 | At the start of each phase, the team identifies the tasks that need to happen. These tasks are entered into the first column.
Creating Non-functional requirement | Elizabeth | 2024-10-01 | Elizabeth | 2024-10-01 | The work is assigned to team members with a deadline. It is recorded in the tasking spreadsheet
Setup a Communication channel | Mohammed | 2024-09-26 | Mohammed | 2024-09-26 | When the work is completed, the team member completing it is recorded.
Creating functional requirement | Adam | 2024-10-01 | Adam | 2024-10-01
A team consists of more than one person working toward a common goal and should include individuals of diverse backgrounds, skills, or perspectives.
an ability to function effectively on a team whose members together provide leadership, create a collaborative and inclusive environment, establish goals, plan tasks, and meet objectives.